## Slide 1
Software Onboarding Process Transformation
v3 Discovery Deep Dive and Implementation Roadmap
Based on 14 stakeholder interviews across Architecture, Product, Security, Risk Management, Vendor Management, Finance, Legal, and Compliance teams. 24 gaps identified across 11 governance domains with actionable 30/60/90/120-day implementation plans.
14 Stakeholder Sessions
11 Governance Domains
24 Gap Findings
120-Day Roadmap
KPMG Confidential
March 2026

## Slide 2
Executive Summary
The software onboarding process spans 6 to 9 months end-to-end, driven by 18 sequential committees, 5+ disconnected intake channels, and critical resource bottlenecks in Security and Legal. The START initiative created centralized awareness but did not integrate underlying team processes.
6-9 mo
CURRENT E2E CYCLE
18
COMMITTEES
335/yr
ASSESSMENTS
24
GAPS IDENTIFIED
Highest-ROI Investment Areas
Parallel Evaluation
Replace 18 sequential committees with 5 parallel evaluation streams. Bounded by slowest SLA, not sequential sum.
Unified Intake + Deal-Killer
Consolidate 5+ channels. Block non-starters at day 1. Route 3 request types differently.
Contract Automation
Automate contract review for the 2-person team handling 30+ contracts/month.
"Somebody needs to be empowered at the firm to say I own this"
-- TPRM Lead
KPMG Confidential
March 2026

## Slide 3
End-to-End Workflow: Current Pain Points
SP1: Intake
3 request types not routed
SP2: Prioritize
Whoever screams loudest
SP3: Evaluate
Sequential DART 3x AI vendor contact
SP4: Contract
2 ppl / 30+ contracts 1.5yr security
SP5: Go-Live
No conditional approval
Critical Bottlenecks
Contract Negotiation
2 people / 30+ contracts monthly. Up to 1.5 years for security exhibits.
Security Review
"Biggest bottleneck... reason our SLA takes 2 weeks." Cannot scale for AI.
Sequential DART
Requester contacts 5-6 teams independently. No visibility into sequence.
AI Governance
60+ items in queue. 3 committees. 3x vendor contact for AI reviews.
What Works Well
Architecture Governance
Dedicated Facilitator pre-screens artifacts, manages follow-ups. Best-practice model.
TPRM Improvement
Reduced DD from 144 to 75 days. 335 assessments/year with 8-person team.
AI Tool Adoption
Cursor AI for diagrams, custom AI agent for pattern conformance scanning.
KPMG Confidential
March 2026

## Slide 4
System Landscape and Integration Gaps
"We have all these systems but none of them talk to each other" -- TPRM Lead
System
Function
Integration Status
ServiceNow (START)
Process intake
Entry point, no downstream integration
Ariba
Registration, NDAs, contracts
API to Oracle only
OneTrust
Risk assessments, tracking, control gaps
Standalone, manual PDF exports
Oracle
Accounts payable
API from Ariba
Confluence + Catfox
Architecture approvals
Plugin-based, no workflow integration
JIRA
Architecture ticket tracking
Per-team, no cross-functional view
Camunda 8 (target)
E2E process orchestration
Not yet deployed
KPMG Confidential
March 2026

## Slide 5
By the Numbers: Quantified Pain
335/yr
ASSESSMENTS
28-29d
RAE ACTUAL (14D TARGET)
75d
DD INTERNAL REVIEW
2 ppl
30+ CONTRACTS/MO
1.5yr
SECURITY EXHIBIT NEGOTIATION
2-3/10
BUSINESS COUNCIL QUORUM
60-90d
COMPETITOR BENCHMARK
18
COMMITTEES (TARGET: 5 STREAMS)
"That team desperately needs automation... The firm needs them to be automated"
-- TPRM Lead (on Legal/Contracts)
KPMG Confidential
March 2026

## Slide 6
Cross-Cutting Process Design
Concierge model, simultaneous engagement, and organizational design patterns that apply across all 11 governance domains.
KPMG Confidential
March 2026

## Slide 7
Process Quarterback / Concierge Model
Architecture Today (Best Practice)
Pre-Screen Artifacts
Remove incomplete items from ARB/SDRB agenda before meeting.
Manage Follow-Ups
Capture action items, track completion, run meetings efficiently.
JIRA Integration
Ticket tracking and domain-based auto-assignment to 4 EA leaders.
Proposed E2E Extension
Single Point of Contact
Eliminates 5-6 team self-navigation for requesters.
Automated DART Formation
Concierge triggers all review streams simultaneously.
Quality Gates at Boundaries
Reject incomplete before wasting SME time.
"If any artifact is not in good order, remove it from the agenda"
-- Architecture Lead
"Exactly like what we're talking about for the quarterback from a broader end-to-end"
-- Consulting Team
KPMG Confidential
March 2026

## Slide 8
Simultaneous Engagement Model
Current: Sequential (weeks to months)
TBC approval
Requester contacts Architecture... wait...
Requester contacts Security... wait...
Requester contacts Compliance... wait...
Requester contacts AI Gov... wait...
Timeline: dependent on requester initiative
Proposed: Parallel (bounded by slowest SLA)
Architecture
HLD review, domain assignment
Security
Tiered assessment by risk category
Compliance
Regulatory review + OneTrust evidence
AI Governance
Consolidated single-stream review
Legal
Contract terms + NDA execution
"I disagree with that because that makes us a bottleneck... there should be simultaneous engagement of all the major players that have a vote"
-- Architecture Lead
KPMG Confidential
March 2026

## Slide 9
3 Request Types and Distributed Pod Model
3 Request Types (New in v3)
Defined Need
Business owner knows requirements, vendor selected. Standard 5-phase path. Most common.
Forced Update
Existing vendor, product changes (on-prem to SaaS, EOL, new AI). Re-evaluation at SP3.
Speculative / Exploratory
Advisory support, no sponsorship. Idea funnel (pre-SP1), NOT standard process.
Distributed Pod Model
Cybersecurity Pod
Own prioritization, meeting frequency, review speed | Central team ensures consistency
Architecture Pod
Technical review cadence, domain assignment | Central team ensures consistency
Legal/Contracts Pod
Template usage, negotiation approach | Central team ensures consistency
AI Governance Pod
AI risk posture, review depth | Central team ensures consistency
TPRM Pod
Assessment methodology, vendor scoring | Central team ensures consistency
"The process never solved the step of requester who's never been through onboarding"
-- Vendor Management Lead
KPMG Confidential
March 2026

## Slide 10
Implementation Roadmap: 30 / 60 / 90 / 120 Days
Days 1-30: Foundation
Map all intake fields, deduplicate Define 3 request types + routing rules NDA timing decision (Sec + Legal) Map 18 committees to 5 streams Draft concierge role description Simultaneous engagement rules Deal-killer no-go list Prioritization scoring w/ capacity Baseline RAE (28d) and DD (75d) metrics Map OneTrust API integration points
Days 31-60: Quick Wins
Unified intake form (3 request types) Completeness quality gate at intake Deal-killer pre-screen active NDA gate between SP1 and SP3 Status notifications at boundaries Async voting for Business Council Single AI questionnaire deployed OneTrust-Camunda integration design Contract template standardization Pilot simultaneous engagement
Days 61-90: Automation
3-pathway routing: Buy/Build/Enable 5 parallel evaluation streams live Concierge orchestration active Tiered security assessment in SP3 AI fast-track piloted (2-week target) OneTrust assessment automation in SP3 Automated baseline security checks AI-assisted pre-screening pilot Finance rework loop in SP4 Capacity-aware routing
Days 91-120: Scale
Exception routing (rapid RA) Pre-onboarding idea funnel Workload visibility dashboard Contract review automation Full deviation reporting Distributed pod model pilot Progressive forms + stage awareness Annual ownership validation Executive KPI reporting Before/after metrics documented
60-70%
Cycle Time Reduction
18 to 5
Sequential to Parallel
3 Pathways
Buy/Build/Enable
Day 1
Non-Starter ID
KPMG Confidential
March 2026

## Slide 11
Intake
Initial request capture, portfolio review, and solution discovery.
KPMG Confidential
March 2026

## Slide 12
Process Model: SP1: Request and Triage
SP1_RequestTriage
Request capture through unified intake gateway, existing solution review, bypass routing for leveraged software, initial triage with 2-day SLA timer, and DMN-driven pathway routing (OB-DMN-2). v3 adds 3 request type routing: Defined Need (standard), Forced Updates (re-evaluation at SP3), Speculative/Exploratory (idea funnel pre-SP1).
KPMG Confidential
March 2026

## Slide 13
Intake: Current State Findings
5+ Disconnected Channels
ServiceNow, REA (~80Q), AI forms, Power Apps, email, feedback platform, advisor tool approvals.
3 Request Types Treated Identically
Defined Need, Forced Updates, Speculative all follow same heavyweight process.
Tool Decay
Financial form shows 2024, locked, password unknown, owner left org.
No Pre-Screen
Obvious no-gos reach SME teams. No deal-killer check.
"You submit a formal intake request so they have trackability"
-- Product Manager
KPMG Confidential
March 2026

## Slide 14
Intake: Recommendations
Unified Intake Gateway (GAP-1)
Single entry absorbs all channels. Dynamic routing by request type. HIGH IMPACT
NDA Gate (GAP-17)
Mandatory NDA before detailed evaluation. Security+Legal aligned. NEW in v3
Deal-Killer Pre-Screen (GAP-16)
DMN-driven no-go list. Reject known non-starters immediately. QUICK WIN
3 Request Type Routing
OB-DMN-2 expanded with requestType. Speculative to idea funnel, Forced Updates skip intake. NEW in v3
30 Days
Map fields NDA timing decision 3 request types
60 Days
Unified form NDA gate Completeness gate
90 Days
Progressive forms Informal channel redirect
120 Days
Exception routing Idea funnel Metrics
KPMG Confidential
March 2026

## Slide 15
Prioritization
Scoring, queue management, and governance decision cadence.
KPMG Confidential
March 2026

## Slide 16
Process Model: SP2: Planning and Routing
SP2_PlanningRouting
Preliminary assessment, backlog management, and DMN-driven pathway routing (OB-DMN-2). v3 adds capacity-aware scoring via OB-DMN-5 with business impact, strategic alignment, urgency, risk tier, and capacity impact inputs producing P1/P2/P3 output.
KPMG Confidential
March 2026

## Slide 17
Prioritization: Current State Findings
No Formal Standard
Teams 'horse trade.' Each requestor views their request as most important.
Whoever Screams Loudest
EVP support pushes reviews down. No effective prioritization possible.
Business Council Quorum
Monthly meetings, 2-3 of 8-10 attend. Evolved to email voting.
Capacity Disconnected
PI planning allocates capacity. Exception requests force pivots.
"If the general pace of onboarding is accelerated, then we could theoretically handle these one-off cases with more capacity"
-- Product Manager
KPMG Confidential
March 2026

## Slide 18
Prioritization: Recommendations
DMN-Driven Scoring (GAP-2)
OB-DMN-5: business impact, alignment, urgency, risk tier, capacity. P1/P2/P3 output. HIGH IMPACT
Async Governance (GAP-24)
Replace monthly meetings with 48-hour async SLA. Email voting formalized. NEW in v3
3-Pathway Routing (GAP-11)
Buy, Build, Enable (Vendor Affinity). Right-sized governance per pathway. HIGH IMPACT
Capacity-Aware Routing
Score includes capacity impact. Route around constrained teams. NEW in v3
30 Days
Capacity impact scoring Business Council quorum fix Async decision rules
60 Days
Async voting deployed Queue position visible
90 Days
Capacity-aware routing Acceleration metrics baseline
120 Days
Queue wait time metrics Capacity utilization Decision cycle time
KPMG Confidential
March 2026

## Slide 19
Funding
Financial analysis, budget approval, and coding matrix workflows.
KPMG Confidential
March 2026

## Slide 20
Process Model: SP2/SP3: Financial Touchpoints
SP2_SP3_Finance
Financial analysis spans 4 phases: SP1 (estimate), SP2 (justification), SP3 (full TCO/ROI), SP4 (final approval). Progressive financial data collection reduces requester burden. v3 adds Enable pathway bypass for Vendor Affinity products that require no org funding.
KPMG Confidential
March 2026

## Slide 21
Funding: Current State Findings
Formal Denial Restarts Process
Minor corrections require full restart. Cannot reroute to FP&A.
Enable Pathway Friction
Vendor Affinity tools require no org funding but validation still required.
Outdated Tools
Finance form locked, password unknown, completed offline.
4-Phase Financial Touchpoints
Financial analysis in SP1, SP2, SP3, SP4. Progressive collection needed.
KPMG Confidential
March 2026

## Slide 22
Funding: Recommendations
Finance Rework Loop (GAP-4)
Minor corrections loop without denial. Pattern matches PDLC retry. MEDIUM
Enable Pathway Bypass
Vendor Affinity products skip funding validation entirely. NEW in v3
FP&A Integration
Direct routing for coding matrix issues. No external email. MEDIUM
Progressive Financial Data
SP1: estimate. SP2: justification. SP3: full TCO/ROI. LOW EFFORT
30 Days
Map financial fields across phases Enable bypass criteria
60 Days
Finance rework loop deployed FP&A direct routing
90 Days
Enable pathway financial bypass active Progressive forms
120 Days
Measure: rework rate Enable pathway adoption
KPMG Confidential
March 2026

## Slide 23
Sourcing / Evaluation
DART formation, committee coordination, and vendor due diligence.
KPMG Confidential
March 2026

## Slide 24
Process Model: SP3: Evaluation and Due Diligence
SP3_EvalDD
5 parallel evaluation streams: Technical Architecture, Security Assessment, Risk/Compliance/Legal, Financial Analysis, Vendor Landscape Assessment. Vendor due diligence questionnaire (830 questions with skip logic). v3 replaces sequential DART formation with simultaneous engagement triggered by concierge. 5-day SLA timer on vendor response.
KPMG Confidential
March 2026

## Slide 25
Sourcing: Current State Findings
Sequential DART Formation
Requester independently contacts 5-6 teams. No visibility into sequence.
ARB + TBC + AI Gov Sequential
Same case presented to multiple committees. Meetings weeks apart.
Security as Primary Bottleneck
Security is our biggest bottleneck. 2-week SLA driver. Understaffed.
Governance Facilitator Excellence
Architecture has dedicated facilitator: pre-screens, removes incomplete items, runs ARB/SDRB.
"I disagree with that because that makes us a bottleneck... simultaneous engagement of all major players"
-- Architecture Lead
KPMG Confidential
March 2026

## Slide 26
Sourcing: Recommendations
Simultaneous Engagement (GAP-19)
Parallel engagement of all review streams. Concierge triggers automatically. HIGH IMPACT
Governance Facilitator Model
Scale Architecture's pre-screening model to E2E. Reject incomplete artifacts. NEW in v3
Domain Auto-Assignment
4 EA leaders route by domain. Auto-assign by bandwidth via OB-DMN-2. NEW in v3
5 Parallel Evaluation Streams
Technical, Security, AI, Compliance, Vendor Landscape simultaneously. HIGH IMPACT
30 Days
ARB/SDRB/TBC scope boundaries Simultaneous engagement rules Concierge role
60 Days
Pilot simultaneous engagement Catfox integration Domain auto-assignment
90 Days
5 streams operational Artifact quality gate Concierge orchestration
120 Days
DART formation time (target: automated) Evaluation cycle time
KPMG Confidential
March 2026

## Slide 27
Cybersecurity
Security assessment, tiered review, and AI review consolidation.
KPMG Confidential
March 2026

## Slide 28
Process Model: SP3: Security Assessment Stream
SP3_Security
Tiered security assessment driven by DMN risk-based categories: local install, platform, hybrid, pre-approved, updates, module additions. Baseline tier (automated checks), Elevated tier (auto + manual), Major tier (full assessment + penetration testing). v3 consolidates 3x AI vendor contact into single stream.
KPMG Confidential
March 2026

## Slide 29
Cybersecurity: Current State Findings
Biggest Bottleneck
Security is the reason SLA takes 2 weeks. Understaffed team.
Cannot Scale for AI
"I need three of me right now" -- specifically for AI reviews.
Zero Automation
All routing manual. No workflow integration. Individual knowledge dependency.
3x Vendor Contact for AI
Tech risk, cybersecurity, TPRM each contact vendors independently.
"Security is our biggest bottleneck... Enterprise architecture would get SLA way down without security constraints"
-- Architecture Lead
KPMG Confidential
March 2026

## Slide 30
Cybersecurity: Recommendations
Tiered Security Assessment (GAP-12)
DMN-driven: Baseline (automated), Elevated (auto+manual), Major (full+pentest). HIGH IMPACT
Risk-Based Categories
6 types: local install, platform, hybrid, pre-approved, updates, module additions. NEW in v3
AI Review Consolidation
Single stream replaces 3x vendor contact. Eliminate redundancy. NEW in v3
NDA Timing Resolution
Security+Legal align on early NDA. Executive decision at Day 30. NEW in v3
30 Days
6 risk-based assessment categories NDA timing resolution Map security capacity
60 Days
Automated baseline checks Tiered assessment DMN NDA gate active
90 Days
Security: Elevated/Major only AI vendor contact consolidated
120 Days
Security review cycle time by tier Baseline automation rate AI queue depth
KPMG Confidential
March 2026

## Slide 31
Enterprise Architecture
Architecture review boards, artifact frameworks, and domain governance.
KPMG Confidential
March 2026

## Slide 32
Process Model: SP3: Architecture Review Stream
SP3_Architecture
Architecture review within SP3 parallel evaluation. ARB (2-week SLA for complex), SDRB (same-day for prepared teams). Artifact framework: HLD pre-contract (all), SD/SYDD post-contract (local), PSS post-contract (enterprise/AI). v3 adds AI-assisted pre-screening and preparation quality gates.
KPMG Confidential
March 2026

## Slide 33
Enterprise Architecture: Current State Findings
ARB 2-Week SLA, SDRB Same-Day
Well-prepared teams get faster reviews. New capabilities are slower.
Artifact Framework
HLD pre-contract (all). SD/SYDD post-contract (local). PSS post-contract (enterprise/AI).
AI Tools Already in Use
Cursor AI for diagrams, custom AI agent for pattern conformance scanning.
Domain Funding Constraints
Architects funded by domains. Under-funding = capacity bottleneck.
"We're trying to use AI to help expedite these reviews"
-- Architecture Lead
KPMG Confidential
March 2026

## Slide 34
Enterprise Architecture: Recommendations
Scale Facilitator Model
Governance Facilitator becomes E2E concierge template. Pre-screen all artifacts. HIGH IMPACT
AI-Assisted Pre-Screening
Leverage existing Cursor/custom agent for pattern conformance automation. NEW in v3
Preparation Quality Gate
Reject incomplete artifacts before ARB. Reduce wasted committee time. NEW in v3
Domain Auto-Assignment
4 EA leaders route by domain. Auto-assign architect by bandwidth. MEDIUM
30 Days
Document ARB/SDRB SLAs Assess AI tools Domain assignment rules
60 Days
AI pre-screening pilot Domain auto-assignment in OB-DMN-2
90 Days
ARB preparation quality gate SDRB fast-track for pre-approved
120 Days
ARB cycle time Preparation rejection rate AI pre-screening accuracy
KPMG Confidential
March 2026

## Slide 35
Compliance
Regulatory alignment, phase-boundary gates, and evidence management.
KPMG Confidential
March 2026

## Slide 36
Process Model: SP3: Compliance Review Stream
SP3_Compliance
Compliance review within SP3 parallel evaluation. Phase-boundary quality gates enforce compliance checks at every transition. OneTrust integration provides automated compliance audit trail. Regulatory annotations on every task: OCC 2023-17, SOX, GDPR, DORA, EU AI Act, NIST CSF 2.0.
KPMG Confidential
March 2026

## Slide 37
Compliance: Current State Findings
End-of-Year Failures
Compliance failures discovered late in year. Reactive not proactive.
OneTrust Evidence Platform
Assessment evidence captured in OneTrust. Control gaps documented.
No Phase-Boundary Gates
Compliance checks not enforced at transitions between phases.
Regulatory Complexity
OCC 2023-17, SOX, GDPR, DORA, EU AI Act all apply. No unified tracking.
KPMG Confidential
March 2026

## Slide 38
Compliance: Recommendations
Consolidated Compliance Stream
Single compliance review in SP3 parallel. Phase-boundary quality gates. HIGH IMPACT
OneTrust Integration
Automated compliance audit trail. Evidence linked to process instances. NEW in v3
Regulatory Annotation
Every task tagged with applicable regulations via Camunda properties. MEDIUM
3-Tier Review Structure
Fast path (single), Committee (quorum), Board (full). DMN-3 routes. MEDIUM
30 Days
Map compliance touchpoints OneTrust evidence capabilities
60 Days
OneTrust compliance evidence mapping
90 Days
Automated compliance audit trail via OneTrust
120 Days
Regulatory traceability dashboard OneTrust data feed
KPMG Confidential
March 2026

## Slide 39
AI Governance
AI risk classification, committee consolidation, and regulatory alignment.
KPMG Confidential
March 2026

## Slide 40
Process Model: SP3: AI Review Stream
SP3_AIReview
AI governance review within SP3 parallel evaluation. Single consolidated stream replaces 3 separate committees. AI risk posture classification via DMN. Fast-track pathway for AI-only reviews targeting 2-week E2E. v3 merges 3+ AI questionnaires into single dataset.
KPMG Confidential
March 2026

## Slide 41
AI Governance: Current State Findings
60+ Items in Queue
AI governance backlog overwhelming. No clear prioritization.
Committee Redundancy
Working Committee + Decision Committee somewhat redundant with TBC.
Questionnaire Proliferation
3 additional AI forms "snuck up" beyond standard DD. Being merged.
3x Vendor Contact
Tech risk, cybersecurity, TPRM independently contact vendors for AI.
"I have no idea why they're there... they just snuck up and I'm really annoyed"
-- TPRM Lead
KPMG Confidential
March 2026

## Slide 42
AI Governance: Recommendations
Consolidate 3 Committees to 1
Single AI review stream. Eliminate redundant presentations. HIGH IMPACT
AI Questionnaire Merger (GAP-23)
Merge 3+ forms into single dataset. TPRM Lead already in progress. NEW in v3
Single Vendor Contact
One AI review stream. Eliminate 3x vendor contact redundancy. NEW in v3
AI Fast-Track (GAP-6)
AI Governance + Security only. 2-week E2E target. HIGH IMPACT
30 Days
Merge 3 AI questionnaires Map committee consolidation Inventory vendor contacts
60 Days
Single AI questionnaire deployed Committee consolidation communicated
90 Days
AI fast-track piloted EU AI Act mapping to DMN
120 Days
AI review cycle time (2wk target) Vendor contact reduction (3x to 1x)
KPMG Confidential
March 2026

## Slide 43
Privacy
Data classification, privacy-by-design, and cross-border requirements.
KPMG Confidential
March 2026

## Slide 44
Process Model: SP1/SP3: Privacy Assessment
SP1_SP3_Privacy
Data classification at intake (SP1) drives privacy routing. Privacy review embedded in SP3 parallel evaluation. OneTrust privacy module available for automated assessments. Cross-border data flow triggers additional assessment requirements.
KPMG Confidential
March 2026

## Slide 45
Privacy: Current State Findings
Embedded Across Teams
Privacy review integrated into multiple team processes.
Data Classification at Intake
Classification questions appear early but not enforced.
Cross-Border Complexity
International data flows require additional assessment.
OneTrust Privacy Module
Privacy capabilities available in existing OneTrust deployment.
KPMG Confidential
March 2026

## Slide 46
Privacy: Recommendations
Data Classification at Intake
Mandatory data classification in SP1 form. Drives privacy routing. MEDIUM
Privacy-by-Design
Privacy controls embedded in architecture review checklist. MEDIUM
OneTrust Privacy Integration
Leverage existing privacy module for automated assessments. NEW in v3
Cross-Border Assessment
Automated triggers for international data flow requirements. LOW
30 Days
Map privacy touchpoints Classification field requirements
60 Days
Data classification mandatory at intake
90 Days
OneTrust privacy integration Privacy-by-design checklist
120 Days
Cross-border automation Privacy compliance rate
KPMG Confidential
March 2026

## Slide 47
Commercial Counsel
Contract lifecycle, negotiation bottleneck, and deviation tracking.
KPMG Confidential
March 2026

## Slide 48
Process Model: SP4: Contracting and Build
SP4_ContractBuild
Contract negotiation, vendor selection finalization, and build/buy execution. Buy path: refine solution, PoC, technical risk, negotiate, await contract, finalize. Build path: define build requirements, PDLC execution. v3 elevates contract automation to critical priority: 2 people handling 30+ contracts/month.
KPMG Confidential
March 2026

## Slide 49
Commercial Counsel: Current State Findings
Dumpster Fire #1
2 people negotiating 30+ contracts monthly. 4 years unsustainable.
No Deviation Reporting
No reportable format for contract deviations. Unknown compliance for older contracts.
Security Exhibits: 1.5 Years
Contract negotiation for security terms can take up to 18 months.
Sourcing Doesn't Source
Sourcing dept manages contract lifecycle, not actual sourcing.
"That team desperately needs automation... The firm needs them to be automated"
-- TPRM Lead
KPMG Confidential
March 2026

## Slide 50
Commercial Counsel: Recommendations
Contract Review Automation (GAP-20)
Automated review for standard terms. Critical priority. HIGH IMPACT / NEW
OneTrust Deviation Tracking
Control gaps documented, risk acceptance tracked in OneTrust. NEW in v3
Template Standardization
Standard contract templates reduce negotiation cycles. MEDIUM
Legacy Compliance Audit
Compliance status for older contracts retroactively assessed. NEW in v3
30 Days
Quantify contract backlog Deviation tracking requirements Automation criteria
60 Days
Contract template standardization OneTrust deviation tracking pilot
90 Days
Automated contract review for standard terms Deviation reporting
120 Days
Contract cycle time Deviation tracking coverage Manual review reduction
KPMG Confidential
March 2026

## Slide 51
TPRM
Third-party risk management, vendor due diligence, and OneTrust integration.
KPMG Confidential
March 2026

## Slide 52
Process Model: SP3: Vendor Due Diligence
SP3_VendorDD
830-question vendor questionnaire with skip logic. Vendor completion avg 30 days. Internal review 75 days (down from 144 in 2019). RAE: 80 questions, 28-29 day actual vs 14-day target, 335 assessments/year with 8-person team. v3 adds OneTrust integration for assessment automation and shift-left strategy.
KPMG Confidential
March 2026

## Slide 53
TPRM: Current State Findings
System Landscape Fragmented
ServiceNow, Ariba, OneTrust, Oracle. Manual PDF transfers between systems.
RAE 2x Target
80 questions, 28-29 day actual vs 14-day target. 335 assessments/year.
DD: 830 Questions, 75 Days
Vendor completion 30 days. Internal review 75 days (down from 144).
Process Ownership Vacuum
Half a person assigned. No clear accountability or communication.
"Somebody needs to be empowered at the firm to say I own this"
-- TPRM Lead
KPMG Confidential
March 2026

## Slide 54
TPRM: Recommendations
Empowered Process Owner (GAP-18)
Dedicated owner with authority. 1 workflow manager + 2-3 PMs. HIGH IMPACT
Shift-Left Strategy
Mini-RFP tools, standard questions upfront, self-service for business users. NEW in v3
OneTrust Integration (GAP-21)
Zeebe service tasks for assessment automation. TPRM module for vendor DD. NEW in v3
Competitor Benchmarking
Target 60-90 day E2E matching less-mature competitors. MEDIUM
30 Days
Map OneTrust API integration Shift-left question inventory Baseline metrics
60 Days
OneTrust-Camunda integration design Shift-left mini-RFP pilot
90 Days
OneTrust assessment automation in SP3 DD skip logic optimized
120 Days
RAE cycle time (14d target) DD cycle time OneTrust automation rate
KPMG Confidential
March 2026

## Slide 55
OneTrust Integration Architecture
Integration Flow (Camunda 8 / Zeebe)
1. Create Assessment
Zeebe Service Task triggers OneTrust Assessment Automation API
2. Assessor Completes
Risk questionnaire (RAE) completed in OneTrust by assigned assessor
3. Retrieve Results
Zeebe Service Task retrieves assessment output via API
4. DMN Routing
Process variables (riskScore, riskTier, complianceFindings[]) feed DMN routing
Two Integration Points
SP3: Risk Assessment
OneTrust Assessment Automation manages questionnaires. Results pulled via API, feed DMN routing.
SP3: Vendor Due Diligence
OneTrust TPRM module. 830-question vendor questionnaire with skip logic.
SP4: Contract Deviations
OneTrust control gap documentation. Deviation tracking, risk acceptance.
Process Variable Mapping
riskScore
Numeric risk score from OneTrust assessment
riskTier
High / Limited / Minimal -- drives DD depth
complianceFindings[]
Array of regulatory gaps requiring remediation
controlGapCount
Count of deviations for contract review routing
Regulatory Alignment: OCC 2023-17 | NIST CSF 2.0 | DORA | SOX
Auth: OAuth2 (client_id/secret), tenant-specific hostname (https://{tenant}.my.onetrust.com)
KPMG Confidential
March 2026

## Slide 56
Staffing and Resource Model
"If we want this to really click... I can't have the architect review group being a critical portion with only two people" -- TPRM Lead
Function
Current Staffing
Workload
Gap
Risk/DD Team
8 people
335 assessments/year
At capacity -- doubled output while cutting timeline
Legal/Contracts
2 people
30+ contracts/month
Critical -- "dumpster fire"
Architecture
2-3 people
Recently reduced
Funding-constrained by domains
Security Architecture
~1 person for AI
"Need three of me"
Cannot scale for AI review volume
Vendor Management
6 total, 2 at 50%
Full process facilitation
No formal allocation
Technology Vendor Mgmt
1 person part-time
Full START process
Inadequate for scope
KPMG Confidential
March 2026

## Slide 57
Measurement Dashboard: Baseline vs. Day 120 Target
Metric
Baseline (Current)
Day 120 Target
E2E cycle time (standard)
6-9 months
60-90 days
E2E cycle time (Enable)
Same as standard
30 days
E2E cycle time (AI fast-track)
Same as standard
14 days
RAE completion
28-29 days
14 days
DD internal review
75 days
30 days
Security review (Baseline tier)
2 weeks
Same-day (automated)
Form completion rate
Unknown
90%+ first-pass
Contract cycle time
Varies (up to 1.5yr)
90 days standard
Business Council decision
Monthly + email
48-hour async SLA
Queue transparency
None
Real-time dashboard
KPMG Confidential
March 2026

## Slide 58
Next Steps
1. Executive Alignment
Present discovery findings and v3 roadmap to executive sponsors. Resolve NDA timing, committee consolidation, and process ownership decisions.
2. Standards Definition
Finalize 3 request types, 6 security categories, prioritization scoring formula, and 3-pathway routing rules. Name owners for every Day 60 deliverable.
3. Quick Wins (Day 60)
Deploy unified intake form, completeness gate, deal-killer pre-screen, NDA gate, and status notifications. Pilot simultaneous engagement.
4. Full Operation (Day 120)
5 parallel streams, OneTrust integration, contract automation, distributed pod model, and executive KPI reporting with before/after metrics.
KPMG Confidential
March 2026