## Slide 1
Software Onboarding
30-Day Process Improvement Plan
Zero technology changes. 7 organizational decisions that cut cycle time in half.
6+ mo
CURRENT AVG CYCLE TIME
3-4 mo
TARGET AFTER 30 DAYS
7
PROCESS CHANGES / NO TECHNOLOGY

## Slide 2
1
Why Onboarding Takes 6+ Months
Three root causes drive 80% of the delay
#1
18 Sequential Committees
Every request passes through up to 18 review committees one at a time. Security waits for Legal. Legal waits for Compliance. A 5-day review becomes 90 days of elapsed time.
#2
No Single Point of Accountability
Nobody owns elapsed time. Each reviewer owns their piece, but nobody tracks the overall request. When it stalls, no one notices for weeks.
#3
Everything Gets Full Treatment
A $10K SaaS renewal with no regulated data gets the same 9-reviewer due diligence as a $2M AI platform handling regulated data. Low-risk renewals and high-risk AI deployments carry fundamentally different risk profiles, yet both sit in the same queue.
Week 1-2: Stop the Bleeding (#1-3)
Week 2-3: Create Rhythm (#4-5)
Week 3-4: Measure & Adjust (#6-7)
Confidential

## Slide 3
2
Week 1-2: Stop the Bleeding
Three changes that can start on Day 1
#1
Appoint Onboarding Quarterbacks (Day 1)
Assign 2-3 dedicated facilitators who own each request end-to-end. Track where every active request sits, chase non-responsive reviewers, escalate stalls after 48 hours, report weekly to leadership. IMPACT: Visibility alone cuts delays
#2
Kill Sequential Reviews, Run Parallel (Day 3)
Send the review package to each reviewer as soon as their prerequisite data is ready. Reviewers work in parallel whenever possible, but no one is asked to start until their required intake information is complete. IMPACT: Compresses Due Diligence from 8-12 weeks to 2-3 weeks
#3
Paper Pre-Screen (Mini RFP)
1-page intake form with 5 deal-killers before pipeline entry: Budget approval? Executive sponsor (VP+)? Regulated data? Existing contract? Realistic go-live? If first two are "No", request does not enter. IMPACT: Filters 20-30% at intake
Confidential

## Slide 4
3
Week 2-3: Create Rhythm
Two structural changes that create predictability
#4
#4 Tiered Review: Not Everything Gets Full Treatment
Score each request across 6 dimensions (1-3 pts each), then route by tier.
Tier | Score | Reviewers | SLA
Fast-Track | 6-8 pts | Quarterback + 1 reviewer | 5 days
Standard | 9-13 pts | 4 reviewers parallel | 15 days
Enhanced | 14-18 pts | All 9 reviewers + exec briefing | 25 days
Dimensions: Data Sensitivity, Vendor Criticality, Financial Exposure, Integration Complexity, AI/ML Usage, Regulatory Exposure
IMPACT: 40-50% move to Fast-Track
#5
#5 Weekly Prioritization Committee (30 min max)
Time-boxed agenda with strict ownership.
Topic | Duration
Pipeline Summary | 2 min
SLA Breaches | 10 min
At-Risk Requests | 8 min
New Intake | 5 min
Decisions Needed | 5 min
IMPACT: Decisions in <5 days vs 2-4 weeks
Confidential

## Slide 5
4
Week 3-4: Measure & Adjust
Two mechanisms that create accountability and feedback
#6
#6 Visible Kanban Board
Six columns. Every active request is a card. Color by age (green/yellow/red). Columns: Intake | Sourcing/Procurement | Due Diligence | Gov Review | Contracting | Go-Live Each card shows: Software name, requester, quarterback, day count, SLA status. IMPACT: Social pressure + visibility drives action
#7
#7 SLA Deadlines with Escalation
Every phase gets a target. Every target has consequences.
Phase | SLA | Warning | Level 1 | Level 2
Quarterback | 2 days | 50% | 100% | 140%
Prioritization Committee | 5 days | 50% | 100% | 140%
Due Diligence | 10 days | 50% | 100% | 140%
Gov Review | 5 days | 50% | 100% | 140%
Contracting | 7 days | 50% | 100% | 140%
Go-Live | 5 days | 50% | 100% | 140%
Level 1: Reviewer's manager | Level 2: CISO / CRO / CFO IMPACT: Accountability where none exists
Confidential

## Slide 6
5
Expected 30-Day Results
Measurable outcomes from 7 process changes
Metric | Current |  | 30-Day Target
Avg Cycle Time | 6+ months | → | 3-4 months
Requests in Limbo | Unknown | → | 100% visible
Reviewer Bottleneck | Hidden | → | Identified by name/team
Low-Value Filtering | ~30% unfiltered | → | Filtered at intake
Decision Latency | 2-4 weeks | → | <5 days
#2 Parallel Reviews
Single biggest lever. Engage reviewers as soon as their prerequisite data is ready. No budget, no technology, no reorg.
#4 Tiered Routing
Stops the one-size-fits-all problem. 40-50% of requests bypass the full review committee entirely.
#1 Quarterback Role
Creates ownership where none exists. A single person tracking elapsed time and chasing blockers changes behavior instantly.
Confidential

## Slide 7
6
The Quarterback Toolkit
8 ready-to-use forms and templates
1
Intake Pre-Screen
2
Risk Tier Classification
3
Request Tracking Board
4
Parallel Review Kickoff
5
Weekly Prioritization Committee
6
SLA Escalation Playbook
7
Phase Transition Checklists
8
Close-Out Form
The process improvement comes first. The technology enforces it later.
Confidential

## Slide 8
7
Toolkit #1: Intake Pre-Screen Form
Deal-Killer Checklist
☐ Budget approval obtained (Minimum VP-level sign-off) ☐ Executive sponsor identified (VP+ level) ☐ Data classification determined (sensitive data identified) ☐ Existing contract or vendor relationship documented ☐ Realistic go-live date (>30 days from intake) If either of the first two fail, request does not enter the pipeline.
Data Classification
☐ Contains sensitive or regulated data ☐ Contains financial or payment data ☐ Subject to GDPR / CCPA ☐ Contains proprietary / trade secret data
Quarterback Decision
Options: • Proceed to Risk Scoring • Return to Requester (Incomplete) • Reject (Deal-Killer Failed) • Redirect to Existing Contract
Confidential

## Slide 9
8
Toolkit #2: Risk Tier Classification
Dimension | 1 (Low) | 2 (Medium) | 3 (High)
Data Sensitivity | Public data only | Internal / confidential | Sensitive / Regulated
Vendor Criticality | Commodity / replaceable | Important but alternatives | Critical / sole-source
Financial Exposure | <$50K annual | $50K-$500K annual | >$500K annual
Integration Complexity | Standalone SaaS | API integration | Deep system integration
AI/ML Usage | No AI/ML | AI-assisted features | Core AI/ML decision-making
Regulatory Exposure | No regulated activity | Indirect regulatory scope | Directly regulated
Fast-Track: 6-8 pts
Quarterback + 1 designated reviewer. 5-day SLA.
Standard: 9-13 pts
4 reviewers in parallel. 15-day SLA.
Enhanced: 14-18 pts
All 9 reviewers + executive briefing. 25-day SLA.
Confidential

## Slide 10
9
Toolkit #6: SLA Escalation Playbook
Phase | SLA Target | 50% Warning | 100% Level 1 | 140% Level 2
Triage | 2 days | Day 1 | Day 2: Reviewer's Manager | Day 3: CISO
Planning | 5 days | Day 2-3 | Day 5: Reviewer's Manager | Day 7: CRO
Due Diligence | 10 days | Day 5 | Day 10: Reviewer's Manager | Day 14: CISO/CRO
Gov Review | 5 days | Day 2-3 | Day 5: Committee Chair | Day 7: CFO
Contracting | 7 days | Day 3-4 | Day 7: Legal Lead | Day 10: GC
Go-Live | 5 days | Day 2-3 | Day 5: Tech Lead | Day 7: CTO
Level 0: Friendly Reminder (50%)
Reminder email to reviewer with due date and offer of support.
Level 1: Formal Escalation (100%)
Notification to reviewer and their manager. SLA breached, require completion by EOD or written explanation.
Level 2: Executive Escalation (140%)
Notification to CISO/CRO/CFO. Business impact documented, requesting executive intervention within 48 hours.
Confidential

## Slide 11
10
Toolkit #7: Phase Transition Checklists
Intake to Due Diligence
☐ Pre-screen form completed [Quarterback] ☐ Deal-killers cleared (all 5) [Quarterback] ☐ Risk tier score calculated [Quarterback] ☐ Executive sponsor confirmed [Requester] ☐ Review package assembled [Quarterback]
Due Diligence to Gov Review
☐ All assigned reviews complete [Quarterback] ☐ No outstanding blockers [Reviewers] ☐ Consolidated findings documented [Quarterback] ☐ Risk summary prepared [Risk] ☐ Governance packet submitted [Quarterback]
Gov Review to Contracting
☐ Governance approval obtained [Gov Lead] ☐ Conditions documented (if any) [Gov Lead] ☐ Legal notified of pending contract [Quarterback] ☐ Budget confirmed and allocated [Finance] ☐ Contract template selected [Legal]
Contracting to Build/Config
☐ Contract fully executed [Legal] ☐ Vendor onboarded in procurement [Procurement] ☐ Technical requirements documented [Architecture] ☐ Implementation team assigned [PM]
Build/Config to Go-Live
☐ UAT completed and signed off [Business] ☐ Security scan passed [Security] ☐ Data migration validated [Tech Lead] ☐ Training plan executed [PM]
Go-Live to Operations
☐ Go-live approval from sponsor [Sponsor] ☐ Monitoring configured [Operations] ☐ Support contacts established [Quarterback] ☐ SLA actuals documented [Quarterback]
Confidential

## Slide 12
11
When Ready: The Automation Platform
The process improvements above run manually. When the organization is ready, these tools enforce and accelerate them.
Task Worker
Live Camunda 8 task management with dynamic JSON form rendering, persona-based filtering, auto-fill defaults. 5-phase process flow visualization.
Process Owner Dashboard
Real-time KPIs: active instances, cycle time, SLA breaches, task backlog. Phase distribution chart, sortable instance table, 10-second auto-refresh.
Mini RFP Pre-Screen
9-step self-service wizard for vendor pre-screening (SP0). Deal-killer alerts, vendor waiting screen with Day 3/7/11 reminders, scoring dashboard.
Concierge Dashboard
Unified navigation hub connecting all showcase applications with role-based access and persona-driven views.
Confidential

## Slide 13
12
Technical Architecture
Camunda 8 Cloud (SaaS)
• Zeebe Engine: Process orchestration, BPMN execution • Tasklist: Human task management API • Operate: Process monitoring, incident management Express.js Gateway (localhost:3847) • OAuth2 client credentials authentication • REST API proxy to Camunda Cloud • zbctl-managed token auto-refresh
Process Configuration
• Process ID: Process_Onboarding_v8 • JSON Forms: 48 form definitions • DMN Tables: 8 decision tables • Personas: 7 lane-based roles Integration Points: • OneTrust TPRM • Jira SLA Project • Camunda Operate • zbctl CLI Cluster: sla-onboarding-dev | us-east-1 | Camunda 8.8+
Confidential

## Slide 14
13
5-Phase Onboarding Lifecycle
SP1 Request & Triage
→
SP2 Planning & Routing
→
SP3 Evaluation & DD
→
SP4 Contracting & Build
→
SP5 UAT & Go-Live
9+1 Governance Lanes
Business
Governance
Contracting
Technical Assessment
AI Review
Compliance
Oversight
Automation
Vendor Response
8 DMN Decision Tables
DMN-1: Risk Tier Classification
DMN-2: Pathway Routing
DMN-3: Governance Review Routing
DMN-4: Automation Tier Assignment
DMN-5: Agent Confidence Escalation
DMN-6: Change Risk Scoring
DMN-7: Vulnerability Remediation
DMN-8: Monitoring Cadence Assignment
Confidential

## Slide 15
14
Next Steps
This Week
• Identify 2-3 Quarterback candidates • Schedule first weekly stand-up • Print and distribute pre-screen forms • Inventory all active requests
This Month
• Run parallel reviews on next 3 requests • Classify entire backlog by risk tier • Publish tracking board where leadership walks by • Measure baseline cycle time
This Quarter
• Measure cycle time reduction vs baseline • Pilot Camunda 8 automation on Fast-Track tier • Expand to additional governance domains • Document wins for executive sponsor
The process improvement comes first. The technology enforces it later.
Confidential