## Slide 1
Software Onboarding
30-Day Process Improvement Plan
Zero technology changes — 7 organizational decisions that cut cycle time in half
6-9 months
Current Avg Cycle Time
3-4 months
Target After 30 Days
7 changes
Process Changes No Technology
Financial Services • Software Onboarding Lifecycle

## Slide 2
The Problem: Why Onboarding Takes 6-9 Months
Three root causes account for 80% of elapsed time. None require technology to fix.
18 Sequential Committees
Every request passes through up to 18 review committees one at a time. Security waits for Legal. Legal waits for Compliance. Compliance waits for Architecture. A 5-day review becomes 5 x 18 = 90 days of elapsed time, even though each reviewer only spends a few hours. The reviews themselves aren't slow — the sequencing is.
No Single Point of Accountability
Nobody owns elapsed time. Each reviewer owns their piece, but nobody tracks the overall request from intake to go-live. When a request stalls, no one notices for weeks. The requester calls around asking "where is my request?" and gets transferred between teams. The Sherpa role solves this — one person owns the clock.
Everything Gets Full Treatment
A $10K SaaS renewal with an existing vendor gets the same 9-reviewer due diligence as a $2M AI platform from a brand new vendor. Roughly 40-50% of requests could be fast-tracked with minimal review, freeing reviewer capacity for the requests that actually need scrutiny. Tiered routing fixes this on day one.
The 30-Day Plan: Three Phases of Change
Week 1-2
#1-3
Stop the Bleeding
Assign Sherpas, run parallel reviews, pre-screen intake
Week 2-3
#4-5
Create Rhythm
Tier routing, weekly governance stand-up
Week 3-4
#6-7
Measure & Adjust
Visible tracking board, enforced SLA deadlines

## Slide 3
WEEK 1-2
Stop the Bleeding
Three changes in the first two weeks that immediately impact cycle time.
1
Appoint Onboarding Sherpas (Day 1)
Assign 2-3 people as dedicated facilitators who own each request end-to-end. The Sherpa tracks where every active request sits, chases reviewers who haven't responded, escalates stalls after 48 hours, and reports weekly to leadership on cycle time. Impact: Immediately surfaces where requests are stuck. Visibility alone cuts delays.
2
Kill Sequential Reviews — Run Parallel (Day 3)
When a request enters Due Diligence, the Sherpa sends the package to ALL reviewers simultaneously with a shared deadline (e.g., 5 business days). No reviewer waits for another to finish first. Impact: Compresses the longest phase from 8-12 weeks to 2-3 weeks. This single change is worth 2-3 months of cycle time.
3
Implement a Paper Pre-Screen (Mini RFP on Paper)
Before a request enters the formal pipeline, require a 1-page intake form with 5 deal-killer questions: • Is there budget approval? • Is there a business sponsor (VP+ level)? • Does it touch regulated data (PII/PHI/financial)? • Is there an existing contract/vendor relationship? • What's the target go-live? If the first two are "No", the request doesn't enter the pipeline. Today, requests that will never be approved consume weeks of committee time. Impact: Filters out 20-30% of requests before they consume any reviewer bandwidth.

## Slide 4
WEEK 2-3
Create Rhythm
Establish the operating cadence that makes the process predictable.
4
Tiered Review — Not Everything Gets the Full Treatment
Establish 3 risk tiers on paper (maps to DMN_RiskTierClassification):
Score | Tier | Reviewers Required | Target SLA | Escalation Path
6-8 pts | FAST-TRACK | Sherpa + 1 reviewer (Security or Compliance) | 5 business days | Sherpa's manager after Day 3
9-13 pts | STANDARD | 4 key reviewers in parallel (Security, Compliance, Legal, Tech Architecture) | 15 business days | Governance lead after Day 10
14-18 pts | ENHANCED | All 9 reviewers in parallel + executive briefing | 25 business days | CISO/CRO after Day 15
Today, a $10K SaaS renewal gets the same scrutiny as a $2M AI platform. 40-50% of requests move to Fast-Track, freeing reviewer capacity for what matters.
5
Weekly Governance Stand-Up (30 minutes max)
Replace monthly committee meetings with a weekly 30-minute stand-up:
Time Box | Agenda Item | Description | Owner
2 min | Pipeline Summary | How many requests total? How many in each phase? How many breached SLA? | Sherpa
10 min | SLA Breaches | Walk through EACH breached request. What is blocking? Who needs to act? Decision: escalate, extend, or kill? | Sherpa + Blockers
8 min | At-Risk Requests | Requests approaching SLA deadline (within 2 business days). What's needed to close on time? | Sherpa + Reviewers
5 min | New Intake | New requests this week. Quick tier assignment and reviewer identification. | Sherpa
5 min | Decisions Needed | Any go/no-go decisions the committee needs to make right now? | Governance Lead

## Slide 5
WEEK 3-4
Measure & Adjust
Make progress visible and create accountability through deadlines.
6
Publish a Visible Kanban Board
Put every active request on a physical board or simple spreadsheet with columns: Intake → Triage → Due Diligence → Governance Review → Contracting → Go-Live Color-code by age: GREEN (on track), YELLOW (approaching SLA), RED (breached). Update weekly. Post it where leadership walks by. Impact: Social pressure and visibility. When leadership can see that 6 requests have been stuck in "Due Diligence" for 40+ days, things move.
Intake
ONB-007 Slack Enterprise Day 1
Due Diligence
ONB-003 AI Analytics Day 18 (BREACH!)
ONB-005 CRM Tool Day 8
Gov. Review
ONB-002 Snowflake Day 4
Contracting
ONB-001 ServiceNow Day 3
Go-Live
(empty)
7

## Slide 6
WEEK 3-4
7
Set and Enforce SLA Deadlines (with Escalation)
Publish target timelines per phase. The escalation path is the enforcement mechanism — no technology needed, just the Sherpa sending an email: "This review is 3 days past SLA. Escalating per policy."
Phase | SLA Target | Warning At | Level 1 Escalation | Level 2 Escalation
Intake / Triage | 2 business days | Day 1 (50%) | Sherpa's manager (Day 2) | Governance Lead (Day 3)
Planning | 5 business days | Day 3 (60%) | Governance Lead (Day 5) | CRO (Day 7)
Due Diligence | 10 business days | Day 7 (70%) | CISO / CLO (Day 10) | CRO + CFO (Day 14)
Individual Review | 5 business days | Day 3 (60%) | Reviewer's manager (Day 5) | Domain head (Day 7)
Governance Review | 5 business days | Day 3 (60%) | CRO (Day 5) | COO (Day 7)
Contracting | 7 business days | Day 5 (70%) | CLO / CPO (Day 7) | CFO (Day 10)
UAT / Go-Live | 5 business days | Day 3 (60%) | Project Sponsor (Day 5) | CTO (Day 7)
Impact: Creates accountability where none exists today. Decisions that currently wait 2-4 weeks for the next committee meeting happen within 5 days.

## Slide 7
Expected 30-Day Results
Conservative estimates based on peer financial services implementations.
Metric | Current State | After 30 Days | Driver
Avg Cycle Time | 6-9 months | 3-4 months (new requests) | Parallel reviews + tiered routing
Requests in Limbo | Unknown | 100% visible | Tracking board + weekly stand-up
Reviewer Bottleneck | Hidden | Identified by name/team | SLA escalation ladder
Low-Value Requests Consuming Capacity | ~30% | Filtered at intake | Pre-screen deal-killers
Decision Latency | 2-4 weeks (next committee) | <5 days (weekly stand-up) | Weekly governance cadence
The Three Biggest Wins
#2
Parallel Reviews
Compresses Due Diligence from 8-12 weeks to 2-3 weeks. This single change recovers 2-3 months of cycle time per request. The reviews themselves aren't slow — the sequential scheduling is.
#4
Tiered Routing
Moves 40-50% of requests to Fast-Track (5-day SLA vs 25-day). Frees reviewer capacity so Enhanced-tier requests get faster attention too. Net effect: everyone moves faster.
#1
Sherpa Role
One person owns elapsed time per request. Chases reviewers, escalates stalls, reports weekly. Turns "nobody's watching" into "someone is always watching."

## Slide 8
The Sherpa Toolkit
8 ready-to-use forms, templates, and checklists that give the Sherpa a mechanistic, repeatable process from intake to close-out.
1
Intake Pre-Screen
2
Risk Tier Classification
3
Request Tracker
4
Parallel Review Kickoff
5
Weekly Stand-Up
6
SLA Escalation
7
Phase Checklists
8
Close-Out Form
These forms are the manual version of what we'll automate in Camunda. The process improvement comes first — the technology enforces it later.

## Slide 9
S
Onboarding Sherpa Toolkit
Manual Process Forms, Templates & Checklists
Software Onboarding Lifecycle | Financial Services
Zero technology required • Implementable in 30 days • 8 ready-to-use forms

## Slide 10
Toolkit Contents
8 forms and templates that give the Sherpa a mechanistic, repeatable process
1
Intake Pre-Screen Form
Filter requests before they enter the pipeline
2
Risk Tier Classification
Score and route to Fast-Track / Standard / Enhanced
3
Request Tracking Board
Kanban + register for all in-flight requests
4
Parallel Review Kickoff
9-reviewer assignment matrix and kickoff email
5
Weekly Governance Stand-Up
30-minute agenda, notes template, summary email
6
SLA Escalation Playbook
Escalation ladder with 3-level email templates
7
Phase Transition Checklists
Gate checklists for every phase boundary
8
Request Close-Out Form
SLA performance capture and lessons learned
Expected 30-Day Impact
Metric | Current | After 30d | How
Avg Cycle Time | 6-9 months | 3-4 months | Parallel reviews + tiered routing
Requests in Limbo | Unknown | 100% visible | Tracking board + weekly stand-up
Reviewer Bottleneck | Hidden | Named | SLA escalation ladder
Low-Value Filtering | ~0% | 20-30% | Pre-screen deal-killers
Decision Latency | 2-4 weeks | <5 days | Weekly governance stand-up

## Slide 11
FORM 1 OF 8
Intake Pre-Screen Form
Complete BEFORE entering a request into the formal pipeline. ~10 minutes.
Requester Information
Requester Name * Department / BU
Email Date Submitted
Software / Vendor Name *
Request Type * (New Vendor | Existing Vendor | Renewal | Upgrade | Build | Forced Update)
Target Go-Live Date
Business Problem / Need *
Existing Solutions Considered
Deal-Killer Screen
If ANY is "No", request cannot proceed
☐ Budget Approval: Has a budget been identified or pre-approved?
☐ Business Sponsor: Is there an executive sponsor (VP+ level)?
☐ Not a Duplicate: Confirmed not already in-flight or in portfolio?
☐ Organizational Alignment: Aligns with strategic initiative?
☐ Realistic Timeline: Go-live at least 30 days out (60 for new)?
Data Classification (Quick Screen)
Check all that apply — determines risk tier
☐ PII (Personally Identifiable Information)
☐ PHI (Protected Health Information)
☐ Financial transaction data (SOX-relevant)
☐ AI / machine learning models
☐ Critical infrastructure (core banking, payments)
☐ Cloud-hosted by third party
☐ Cross-border data transfer
☐ None of the above
Sherpa Decision
Decision options:
PROCEED — Enter into pipeline
RETURN — Missing information (specify)
REJECT — Deal-killer not met
REDIRECT — Existing solution available
Sherpa Name: ________________________
Notes / Conditions:

## Slide 12
FORM 1 • EMAILS
Intake Email Templates
Copy and customize for common intake communications
Pre-Screen Rejection
Subject: Software Request Pre-Screen - Action Required Hi [Requester Name], Thank you for submitting your request for [Software/Vendor]. After our pre-screen review, we've identified the following items that need to be addressed before we can enter this into the formal onboarding pipeline: [ ] Budget approval from cost center owner [ ] Executive sponsor identified (VP+ level) [ ] Confirmation no existing solution covers this need [ ] Strategic alignment documentation [ ] Realistic timeline (minimum 30 days) Please provide the missing items and resubmit. If this is an emergency or regulatory-mandated change, let me know and we'll route it through our expedited path. [Sherpa Name], Onboarding Facilitator
Request Accepted - Next Steps
Subject: Software Onboarding Request Accepted - [Tracking ID] Hi [Requester Name], Your request for [Software/Vendor Name] has passed pre-screening and is now in our onboarding pipeline. Tracking ID: [ONB-2026-XXX] Risk Tier: [Fast-Track / Standard / Enhanced] Target SLA: [5 / 15 / 25] business days Your Sherpa: [Sherpa Name] Next Steps: 1. I will coordinate with the required review teams 2. You may be contacted for additional details 3. I'll send you weekly status updates every [Day] You can reach me directly with any questions. I'm your single point of contact throughout this process. [Sherpa Name], Onboarding Facilitator

## Slide 13
FORM 2 OF 8
Risk Tier Classification Worksheet
Score each dimension 1-3. Total determines Fast-Track / Standard / Enhanced review level.
Dimension | 1 - Low | 2 - Medium | 3 - High | Score
Data Sensitivity | No PII/PHI, public data | Internal data, limited PII | Regulated (PII/PHI/SOX) | ____
Vendor Criticality | Existing vendor, proven | Known vendor, new product | New vendor, no history | ____
Financial Exposure | Under $50K annual | $50K - $500K annual | Over $500K annual | ____
Integration Complexity | Standalone SaaS | API with non-critical systems | Core banking / payments | ____
AI / ML Usage | No AI components | AI features (analytics) | AI in decisions (credit/fraud) | ____
Regulatory Exposure | No regulatory reqs | Standard (GDPR, SOX) | Multi-reg (OCC, DORA, EU AI) | ____
 |  |  | TOTAL: | ____
Tier Routing Guide
Score | Tier | Reviewers Required | Target SLA | Escalation Path
6-8 | FAST-TRACK | Sherpa + 1 reviewer (Security or Compliance) | 5 days | Sherpa's manager after Day 3
9-13 | STANDARD | 4 reviewers parallel (Security, Compliance, Legal, Tech Arch) | 15 days | Governance lead after Day 10
14-18 | ENHANCED | All 9 reviewers parallel + executive briefing | 25 days | CISO/CRO after Day 15
Override: If ANY single dimension = 3, minimum tier is Standard. AI + Regulatory both = 3 → Enhanced automatically.

## Slide 14
TOOL 3 OF 8
Request Tracking Board
Visual tracker for all active requests. Update weekly. Color-code by SLA status.
Intake
[Request Name]
Day X of Y | Tier
Due Diligence
[Request Name]
Day X of Y | Tier
Gov. Review
[Request Name]
Day X of Y | Tier
Contracting
[Request Name]
Day X of Y | Tier
Go-Live
[Request Name]
Day X of Y | Tier
Active Request Register
Master list — print weekly for the stand-up
ID | Software/Vendor | Requester | Tier | Current Phase | Days In | SLA Target | Status | Blocker
ONB-001 | Snowflake | J. Smith | Std | Due Diligence | 7 | Day 15 | On Track | 
ONB-002 | Custom CRM | A. Jones | Enh | Gov. Review | 12 | Day 25 | At Risk | Waiting on security assessment
ONB-003 | Slack Enterprise | M. Chen | Fast | Contracting | 3 | Day 5 | On Track | 
ONB-004 | AI Analytics | R. Patel | Enh | Due Diligence | 18 | Day 25 | Breached | Legal review overdue 3 days

## Slide 15
FORM 4 OF 8
Parallel Review Kickoff Package
Send to ALL required reviewers simultaneously. Do NOT wait for sequential reviews.
Req'd | Review Domain | Reviewer | Sent Date | Due Date | Status
☑ | Security Assessment Pen testing, vuln scan, architecture |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Tech Architecture Integration, scalability, infrastructure |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Risk Assessment Operational, financial, reputational risk |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Compliance Review Regulatory mapping, control requirements |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Privacy Assessment GDPR/CCPA, data classification, cross-border |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Legal Review Contract terms, IP, liability, indemnification |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Financial Analysis TCO, ROI, budget impact, NPV |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | Vendor Landscape Alternative vendors, market analysis |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue
☐ | AI Governance Model risk, EU AI Act, SR 11-7 |  | ____/____ | ____/____ | Not Sent / Sent / In Review / Complete / Overdue

## Slide 16
FORM 4 • EMAILS
Review Kickoff & Findings
Review Kickoff Email
Subject: REVIEW REQUESTED - [Software] - Due [Date] Hi [Reviewer Name], A software onboarding request requires your [Domain] review. Request ID: [ONB-2026-XXX] Software: [Name and brief description] Vendor: [Name, existing/new] Risk Tier: [Fast-Track / Standard / Enhanced] Your Deadline: [Date - X business days] YOUR REVIEW SCOPE: [Specific questions for this domain] DELIVERABLE: Pass / Conditional Pass / Fail with findings. NOTE: This review runs IN PARALLEL with [N] other reviews. You do NOT need to wait. If you cannot meet the deadline, let me know by [Date + 1] so I can arrange coverage. [Sherpa Name]
Reviewer Findings Summary
Consolidate before presenting to governance committee
Domain | Result | Key Findings / Conditions
Security | Pass / Cond / Fail | 
Tech Arch | Pass / Cond / Fail | 
Risk | Pass / Cond / Fail | 
Compliance | Pass / Cond / Fail | 
Privacy | Pass / Cond / Fail | 
Legal | Pass / Cond / Fail | 
Financial | Pass / Cond / Fail | 
Vendor Landscape | Pass / Cond / Fail | 
AI Governance | Pass / Cond / Fail | 

## Slide 17
TEMPLATE 5 OF 8
Weekly Governance Stand-Up
30-minute maximum. Same time every week. Sherpa facilitates. Status and decisions only — no deep dives.
Time Box | Agenda Item | Description | Owner
2 min | Pipeline Summary | How many requests total? How many in each phase? How many breached SLA? | Sherpa
10 min | SLA Breaches | Walk through EACH breached request. What is blocking? Who needs to act? Decision: escalate, extend, or kill? | Sherpa + Blockers
8 min | At-Risk Requests | Requests approaching SLA deadline (within 2 days). What's needed to close on time? | Sherpa + Reviewers
5 min | New Intake | Any new requests entering the pipeline this week? Quick tier assignment and reviewer identification. | Sherpa
5 min | Decisions Needed | Any go/no-go decisions the committee needs to make right now? Governance approvals waiting? | Governance Lead
Ground Rules: No deep-dive discussions. If a topic needs > 2 minutes, schedule separately. Sherpa publishes action items within 1 hour.
Meeting Notes Template
Meeting Date: ____/____/____ Attendees: ________
SLA Breaches: ID | Blocker | Decision | Owner | Deadline
At-Risk Items: ID | Risk | Mitigation | Owner
Decisions Made: Decision | Rationale | Who needs to know
Action Items: Action | Owner | Due Date
Post-Meeting Summary Email
Subject: Governance Stand-Up Summary - [Date] Pipeline: [N] active | [N] breached | [N] new SLA Breaches: [IDs and decisions] At-Risk: [IDs and needed actions] Decisions: [Made this week] Action Items: [Owner - action - due date] Next stand-up: [Date/Time]

## Slide 18
TEMPLATE 6 OF 8
SLA Escalation Playbook
The Sherpa owns escalation. Do not wait for someone else to notice a breach.
Phase | SLA Target | Warning Sent | Level 1 Escalation | Level 2 Escalation
Intake / Triage | 2 business days | Day 1 (50%) | Sherpa's manager (Day 2) | Governance Lead (Day 3)
Planning | 5 business days | Day 3 (60%) | Governance Lead (Day 5) | CRO (Day 7)
Due Diligence | 10 business days | Day 7 (70%) | CISO / CLO (Day 10) | CRO + CFO (Day 14)
Individual Review | 5 business days | Day 3 (60%) | Reviewer's manager (Day 5) | Domain head (Day 7)
Governance Review | 5 business days | Day 3 (60%) | CRO (Day 5) | COO (Day 7)
Contracting | 7 business days | Day 5 (70%) | CLO / CPO (Day 7) | CFO (Day 10)
UAT / Go-Live | 5 business days | Day 3 (60%) | Project Sponsor (Day 5) | CTO (Day 7)
Three Escalation Email Templates
Level 0: Friendly Reminder
At warning threshold "Quick reminder that your [domain] review is due in [N] days. If you need info or are blocked, let me know so I can help."
Level 1: Formal Escalation
At SLA breach "I'm escalating [ONB-XXX] which has exceeded its SLA in [Phase]. SLA Target: [N] days Actual: [N] days (overdue [N]) Blocker: [specific reason]"
Level 2: Executive
After Level 1 fails "[ONB-XXX] has been stalled for [N] days beyond SLA. Level 1 on [Date] has not resolved. OPTIONS: 1. [Recommended path] 2. [Alternative] 3. Kill the request"

## Slide 19
CHECKLISTS 7 OF 8
Phase Transition Checklists
A request cannot advance until ALL items checked. Sherpa verifies and obtains sign-off.
Phase 1: Intake → Planning
☐ Pre-screen form completed (all deal-killers pass) [Sherpa]
☐ Existing portfolio checked (no duplicate) [Sherpa]
☐ Data classification completed [Sherpa]
☐ Risk tier assigned (Fast-Track / Standard / Enhanced) [Sherpa]
☐ Executive sponsor confirmed [Requester]
☐ Request entered in tracking register [Sherpa]
☐ Requester notified with tracking ID and SLA [Sherpa]
Phase 2: Planning → Due Diligence
☐ Buy vs Build pathway determined [Governance]
☐ NDA executed (if new vendor) [Legal]
☐ Preliminary business analysis documented [Business]
☐ Review team identified based on tier [Sherpa]
☐ Vendor documentation package assembled [Sherpa]
☐ Review kickoff package prepared [Sherpa]
Phase 3: Due Diligence → Gov. Review
☐ ALL required reviews completed (per tier) [Sherpa]
☐ Findings consolidated (pass/cond/fail per domain) [Sherpa]
☐ No unresolved "Fail" findings [Sherpa]
☐ Conditional findings have remediation plans [Reviewers]
☐ Vendor DD response received and evaluated [Procurement]
☐ Governance committee briefing prepared [Sherpa]
Phase 4: Gov. Review → Contracting
☐ Committee vote recorded [Governance]
☐ Conditions documented (if conditional) [Governance]
☐ Rejection communicated (if rejected) [Sherpa]
☐ Approval memo signed [Gov. Lead]
☐ Budget authorization confirmed [Finance]
☐ Contract requirements identified [Legal]
Phase 5: Contracting → Go-Live
☐ Contract fully executed (both parties) [Legal]
☐ SLA terms documented in contract [Legal]
☐ Security controls contractually required [Security]
☐ UAT plan with acceptance criteria [Business]
☐ Implementation timeline agreed [Sherpa]
☐ Conditional items remediated/tracked [Sherpa]
Close-Out: Go-Live → Operations
☐ UAT completed and signed off [Business]
☐ Production deployment completed [IT]
☐ Monitoring and alerting configured [IT/Security]
☐ Onboarding record archived [Sherpa]
☐ Requester notified of completion [Sherpa]
☐ Monitoring cadence assigned (per tier) [Governance]
☐ Contract renewal date flagged [Sherpa]

## Slide 20
FORM 8 OF 8
Request Close-Out Form
Complete when a request reaches a terminal state. This is the permanent record.
Close-Out Summary
Request ID: ONB-____-____ Software: ____________________
Outcome: ☐ Onboarded ☐ Rejected ☐ Withdrawn ☐ Redirected
Risk Tier: ☐ Fast-Track ☐ Standard ☐ Enhanced
Date Submitted: ____/____ Date Closed: ____/____
Total Elapsed Days: ____
SLA Performance
Phase | Target | Actual | Delay Reason
Intake | 2d | ____ | 
Planning | 5d | ____ | 
Due Diligence | 10d | ____ | 
Gov. Review | 5d | ____ | 
Contracting | 7d | ____ | 
Go-Live | 5d | ____ | 
Lessons Learned
Review quarterly to improve the process
What went well?
________________________________________
What caused delays?
________________________________________
Process improvement suggestions:
________________________________________
Close-Out Notification Email
Subject: Onboarding Complete - [Software Name] Hi [Requester], Request ID: [ONB-2026-XXX] Outcome: [Onboarded / Rejected / Withdrawn] Total Duration: [N] business days SLA Met: [Yes / No - overdue by N days] If onboarded: Monitoring: [Team/Person] Review cadence: [Quarterly / Semi-annual / Annual] Contract renewal: [Date] If rejected: Rationale: [Summary] Alternatives: [If applicable] [Sherpa Name], Onboarding Facilitator

## Slide 21
Sherpa Quick Reference Card
Print this page and keep at your desk. One card for the entire lifecycle.
Lifecycle at a Glance
1. INTAKE
2 days
Pre-screen, deal-killers, tier assign
2. PLANNING
5 days
Pathway, NDA, review team ID
3. DUE DILIGENCE
10 days
All reviews IN PARALLEL
4. GOV. REVIEW
5 days
Committee vote
5. CONTRACTING
7 days
Contract execution
6. GO-LIVE
5 days
UAT, deploy, monitor setup
Sherpa Rules
1.
YOU own elapsed time. Nobody else is watching.
2.
NEVER wait for sequential reviews. Send all at once.
3.
ALWAYS set a deadline. No open-ended requests.
4.
ESCALATE at threshold. Not after. Not before.
5.
WEEKLY stand-up is sacred. 30 min, no exceptions.
6.
TRACK everything. If it's not on the board, it doesn't exist.
7.
FILTER early. 1 rejected pre-screen saves 10 reviewer-hours.
8.
CLOSE the loop. Requester hears from you, not silence.
9.
MEASURE cycle time. What gets measured gets improved.
10.
DOCUMENT lessons learned. Every close-out form, every time.
Tier Cheat Sheet
FAST-TRACK
6-8 pts | 5 days | 1 reviewer
STANDARD
9-13 pts | 15 days | 4 reviewers
ENHANCED
14-18 pts | 25 days | 9 reviewers
Escalation Cheat Sheet
At 50-70% of SLA:
Send friendly reminder
At 100% of SLA:
Level 1 → reviewer's manager
At 140% of SLA:
Level 2 → executive (CISO/CRO/CFO)
Key principle:
Be factual, not emotional.
Options, not complaints.